## TestCases
Test Suite/ Scenario | TestCaseID - Name | Priority | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail/Blocked | BUG number
Login Interface | 1 - Correct user name and password | p1 | 1. go to link 2. fill in correct user name 3. fill in correct password 4. press login | username: standard_user parola: secret_sauce | Redirect to product page | Redirect to product page | pass
| 2 - Correct user name and wrong password | p1 | 1. go to link 2. fill in correct user name 3. fill in wrong password 4. press login | username: standard_user parola: secret_apple | Error message "Epic sadface:Username and password do not match any user in this service" | Error message "Epic sadface:Username and password do not match any user in this service" | pass
| 3 - Correct user name and blank passwrod | p1 | 1. go to link 2. fill in correct user name 3. let blank password field 4. press login | username: standard_user parola: blank | Error message “Epic sadface: Password is required” | Error message “Epic sadface: Password is required” | pass
| 4 - Blank user name and password filled in | p1 | 1. go to link 2. fill in correct user name 3. let blank password field 4. press login | username: blank parola: secret_sauce | Error message “Epic sadface: Username is required” | Error message “Epic sadface: Username is required” | pass
Products Page | 5 - Verificare lista de produse- existenta lor (6 produse) | p1 | 1. go to link 2. login with correct username and password 3. check the number of products displayed on the page | username: standard_user parola: secret_sauce | Find 6 products on the page | Find 6 products on the page | pass
| 6 - Detalii produs, in produs individual | p2 | 1. go to link 2. login with correct username and password 3. click on a product name | username: standard_user parola: secret_sauce | Details of the product are shown | Details of the product are shown | pass
| 7 - Testare buton "back to all products" | p1 | 1. go to link 2. login with correct username and password 3. click on a product name 4. click on "back to all products" button | username: standard_user parola: secret_sauce | redirect to all products page | redirect to all products page | pass
| 8 - Sortare lista nume A-Z | p3 | 1. go to link 2. login with correct username and password 3. go to filter 4. sort by name A-Z | username: standard_user parola: secret_sauce | products are shown in alphabetical order | products are shown in alphabetical order | pass
| 9 - Sortare lista nume Z-A | p3 | 1. go to link 2. login with correct username and password 3. go to filter 4. sort by name Z-A | username: standard_user parola: secret_sauce | products are shown in reverse alphabetical order | products are shown in reverse alphabetical order | pass
| 10 - Sortare pret small - largest | p3 | 1. go to link 2. login with correct username and password 3. go to filter 4. sort by name price (low to high) | username: standard_user parola: secret_sauce | products are shown from cheaper to higher price | products are shown from cheaper to higher price | pass
| 11 - Sortare pret largest - small | p3 | 1. go to link 2. login with correct username and password 3. go to filter 4. sort by name price (high to low) | username: standard_user parola: secret_sauce | products are shown from higher price to cheaper | products are shown from higher price to cheaper | pass
| 12 - Adaugare 1 produs in cos | p1 | 1. go to link 2. login with correct username and password 3. add 1 product to cart | username: standard_user parola: secret_sauce | 1. one product is shown in cart 2. "add to cart" button changed in to "remove" button | 1. one product is shown in cart 2. "add to cart" button changed in to "remove" button | pass
| 13 - Adaugare 6 produse in cos | p1 | 1. go to link 2. login with correct username and password 3. add 6 products to cart | username: standard_user parola: secret_sauce | 1. six products are shown in cart 2. "add to cart" button changed in to "remove" button for each individual button | 1. six products are shown in cart 2. "add to cart" button changed in to "remove" button for each individual button | pass
| 14 - Testare butonul "Remove" | p1 | 1. go to link 2. login with correct username and password 3. add 1 product to cart 5. click on "Remove" | username: standard_user parola: secret_sauce | the product disappears from the cart and the "remove" button is changing to "add to cart" | the product disappears from the cart and the "remove" button is changing to "add to cart" | pass
| 15 - Testare buton "About" | p3 | 1. go to link 2. login with correct username and password 3. click on "About" button | username: standard_user parola: secret_sauce | redirect to "testing tool kits" | redirect to "testing tool kits" | pass
| 16 - Testare buton "Logout" | p1 | 1. go to link 2. login with correct username and password 3. click on "Logout" button | username: standard_user parola: secret_sauce | go back to login page | go back to login page | pass
| 17 - Testare buton "Cos de cumparaturi" | p1 | 1. go to link 2. login with correct username and password 3. click on "Cart" button | username: standard_user parola: secret_sauce | display the cart content | display the cart content | pass
| 18 - Accesare poza | p2 | 1. go to link 2. login with correct username and password 3. click on product picture | username: standard_user parola: secret_sauce | Details of the product are shown | Details of the product are shown | pass
Cart | 19 - Testare "Butonul Remove" din cosul de cumparaturi | p1 | 1. go to link 2. login with correct username and password 3. Add product to cart 4. Go to cart 5. Press "remove" button | username: standard_user parola: secret_sauce | Product is removed from cart | Product is removed from cart | pass
| 20 - Testare "Continue Shoping" | p1 | 1. go to link 2. login with correct username and password 3. go to cart 4. press "Continue Shopping" | username: standard_user parola: secret_sauce | Redirect to products page | Redirect to products page | pass
| 21 - Verificare detalii produse din cosul de cumparaturi | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart | username: standard_user parola: secret_sauce | Information about products added to cart and quantity are displayed | Information about products added to cart and quantity are displayed | pass
| 22 - Testare buton "check out" |  | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button | username: standard_user parola: secret_sauce | Redirect to checkout form | Redirect to checkout overview | pass
Check out form | 23 - Testare 'Checkout' cu date corecte client | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Fill in correct credentials for Name, Last name, ZIP Code 7. click "Finish" | username: standard_user parola: secret_sauce prenume: Alina nume: Popescu ZIP: 700320 | Redirect to "checkout overview' | Redirect to "checkout overview' | pass
| 24 - Testare 'Checkout' cu date incomplete client: nume gol | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Leave blank last name field 7. click "Finish" | username: standard_user parola: secret_sauce prenume: blank nume: Popescu ZIP: 700320 | Error message "Last name is required” | Error message "Last name is required” | pass
| 25 - Testare 'Checkout' cu date incomplete client: prenume nume gol | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Leave blank name field 7. click "Finish" | username: standard_user parola: secret_sauce prenume: Alina nume: blank ZIP: 700320 | Error message "First Name is required” | Error message "First Name is required” | pass
| 26 - Testare 'Checkout' cu date incomplete client: ZIP gol | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Leave blank ZIP field 7. click "Finish" | username: standard_user parola: secret_sauce prenume: Alina nume: Popescu ZIP: blank | Error message "“ZIP is required” | Error message "“ZIP is required” | pass
| 27 - Testare buton 'Cancel' din din pagina de checkout. | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Fill in correct credentials for Name, Last name, ZIP Code 7. click "Cancel" | username: standard_user parola: secret_sauce | Redirect back to cart page | Redirect back to cart page | pass
Check out overview | 28 - Testare buton "Cancel" | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Fill in correct credentials for Name, Last name, ZIP Code 7. click "Continue" 8, Click on "cancel" | username: standard_user parola: secret_sauce | Go back to cart | Go back to cart | pass
| 29 - Testare buton "Finish" | p1 | 1. go to link 2. login with correct username and password 3. add product to cart 4. go to cart 5. Press "Checkout" button 6. Fill in correct credentials for Name, Last name, ZIP Code 7. click "Continue" 8, Click "Finish" | username: standard_user parola: secret_sauce | Information message "Thank you for your order" | Information message "Thank you for your order" | pass

## Results
Total tests | Nb of Pass test | Nb of Failed test | Nb. Of Blocked tests | Total test covered | Blocked Tests% | Failed test% | Pass test % | Total test covered
29 | 29 | 0 | 0 | 29 | 0 | 0 | 100 | 100